## Sheet1
submittal closure rate | machinery | IFF Issuance rate | manpower | discipline | fabrication variance | safety incident | rfi closure rate | material PO issuance rate | 2wks ahead SPI | Work Week
0.21951 | 38 | 0.59049 | 28 | Mechanical | 0 | 0 | 0.64706 | 0.066667 | 0.77 | 1
0.2439 | 42 | 0.69059 | 55 | Mechanical | -0.01 | 0 | 0.74359 | 0.2 | 0.8 | 2
0.16129 | 42 | 0.80649 | 49 | Mechanical | -0.0124 | 0 | 0.90476 | 0.2 | 0.76 | 3
0.14545 | 42 | 0.86768 | 36 | Mechanical | -0.037 | 0 | 0.92857 | 0.23529 | 0.69 | 4
0.18605 | 42 | 0.90768 | 57 | Mechanical | -0.0254 | 0 | 0.8913 | 0.2 | 0.6 | 5
0.14085 | 53 | 0.92951 | 58 | Mechanical | -0.0492 | 0 | 0.91837 | 0.2 | 0.49 | 6
0.13158 | 53 | 0.95668 | 58 | Mechanical | -0.0981 | 0 | 0.92308 | 0.29412 | 0.44 | 7
0.14103 | 53 | 0.98692 | 58 | Mechanical | -0.1448 | 0 | 0.94444 | 0.29412 | 0.44 | 8
0.15385 | 53 | 0.994 | 74 | Mechanical | -0.01863 | 0 | 0.93103 | 0.29412 | 0.44 | 9
0.17073 | 65 | 0.99431 | 89 | Mechanical | -0.2261 | 0 | 0.91935 | 0.41176 | 0.42 | 10
0.16279 | 65 | 0.95241 | 91 | Mechanical | -0.2827 | 0 | 0.9375 | 0.41176 | 0.45 | 11
0.16279 | 65 | 0.95262 | 121 | Mechanical | -0.3168 | 0 | 0.92857 | 0.5 | 0.47 | 12
0.17978 | 65 | 0.95704 | 122 | Mechanical | -0.3168 | 0 | 0.94521 | 0.47059 | 0.49 | 13
0.17582 | 65 | 0.9602 | 142 | Mechanical | -0.0021 | 0 | 0.94667 | 0.5 | 0.48 | 14
0.16842 | 65 | 0.96611 | 166 | Mechanical | -0.011 | 0 | 0.92208 | 0.5 | 0.52 | 15
0.16842 | 65 | 0.97032 | 181 | Mechanical | -0.0351 | 0 | 0.87654 | 0.5 | 1 | 16
0.16842 | 65 | 0.97032 | 161 | Mechanical | -0.0665 | 0 | 0.90361 | 0.5 | 1 | 17
0.16842 | 65 | 0.97246 | 181 | Mechanical | -0.0421 | 0 | 0.92857 | 0.41176 | 1 | 18
0.21212 | 65 | 0.97205 | 206 | Mechanical | -0.0287 | 0 | 0.81522 | 0.41176 | 1 | 19
0.23 | 65 | 0.97289 | 206 | Mechanical | -0.0088 | 0 | 0.93684 | 0.41176 | 0.97 | 20
0.23 | 65 | 0.97289 | 206 | Mechanical | -0.0859 | 0 | 0.94737 | 0.68421 | 0.95 | 21
0.2 | 65 | 0.97289 | 215 | Mechanical | -0.1642 | 1 | 0.94 | 0.68421 | 0.96 | 22
0.2 | 65 | 0.9832 | 222 | Mechanical | -0.27 | 0 | 0.93069 | 0.9375 | 0.94 | 23
0.26923 | 62 | 0.9826 | 222 | Mechanical | -0.2764 | 0 | 0.94118 | 0.9375 | 0.92 | 24
0.28 | 62 | 0.96365 | 223 | Mechanical | -0.2764 | 0 | 0.95146 | 0.8125 | 0.93 | 25
0.25926 | 62 | 0.95502 | 223 | Mechanical | -0.2764 | 0 | 0.97087 | 0.8125 | 0.9 | 26
0.37037 | 62 | 0.96365 | 175 | Mechanical | -0.2764 | 0 | 0.95283 | 0.75 | 0.88 | 27
0.37037 | 58 | 0.95502 | 160 | Mechanical | -0.2275 | 0 | 0.93694 | 0.8 | 0.86 | 28
0.42308 | 58 | 0.96365 | 179 | Mechanical | -0.2377 | 0 | 0.9386 | 0.70588 | 0.85 | 29
0.5 | 58 | 0.96365 | 286 | Mechanical | -0.4157 | 0 | 0.92437 | 0.70588 | 0.84 | 30
0.53846 | 58 | 0.96365 | 335 | Mechanical | -0.4122 | 0 | 0.9322 | 0.70588 | 0.83 | 31
0.5 | 58 | 0.96365 | 269 | Mechanical | -0.4241 | 0 | 0.95082 | 0.70588 | 0.82 | 32
0.5 | 58 | 0.96365 | 272 | Mechanical | -0.3932 | 0 | 0.96124 | 0.70588 | 0.82 | 33
0.5 | 163 | 0.4963 | 454 | Mechanical | -0.3618 | 0 | 0.97037 | 0.66667 | 0.81 | 34
0.5 | 163 | 0.72593 | 454 | Mechanical | -0.3443 | 0 | 0.98529 | 0.66667 | 0.81 | 35
0.5 | 163 | 0.726 | 454 | Mechanical | -0.34 | 0 | 0.99 | 0.67 | 0.8 | 36
0.53125 | 185 | 0.72593 | 482 | Mechanical | -0.3304 | 0 | 0.9927 | 0.66667 | 0.81 | 37
0.53125 | 185 | 0.8 | 466 | Mechanical | -0.3205 | 0 | 0.96552 | 0.70588 | 0.82 | 38
0.5625 | 233 | 0.8 | 474 | Mechanical | -0.3074 | 0 | 0.97333 | 0.70588 | 0.83 | 39
0.53125 | 185 | 0.8 | 466 | Mechanical | -0.3205 | 0 | 0.96552 | 0.70588 | 0.84 | 40
0.5625 | 233 | 0.8 | 474 | Mechanical | -0.3074 | 0 | 0.97333 | 0.70588 | 0.85 | 41
0.66667 | 267 | 0.82963 | 501 | Mechanical | -0.0192 | 0 | 0.97436 | 0.71 | 0.86 | 42
0.63636 | 267 | 0.82963 | 494 | Mechanical | -0.067 | 0 | 0.975 | 0.71 | 0.87 | 43
0.61765 | 267 | 0.82963 | 473 | Mechanical | -0.0874 | 0 | 0.97546 | 0.75 | 0.88 | 44
0.61765 | 267 | 0.82963 | 481 | Mechanical | -0.11 | 0 | 0.96988 | 0.75 | 0.89 | 45

## Sheet2
material receive rate = sum received/sum total
qaqc closure rate = closed/total use weekly
submittal closure rate = sum(returned to date)/sum(submitted to date + returned to date)
safety induction use YTD #
manpower use actual #
SPI use accumulative SPI at the week start